## Slide 1
USF · Center for Innovation, Technology & Aging
May 18, 2026
WEEK 1 · PLANS PRESENTATION
Robotic O₂
Generator
Carrier.
Team one
Olga · Aibek · Chi Vo
Supervisor: Dr. William Kearns
Hackathon: Prof. Yu Sun

## Slide 2
The brief
02 / 11
IN ONE SENTENCE
Teach a quadruped robot to follow a person up and down stairs while carrying an oxygen generator.
USF Hackathon 2026
01 · Brief

## Slide 3
Scope
03 / 11
WHERE WE PLUG IN
The robot already walks and follows on flat ground. Stairs are the gap.
ALREADY BUILT
OUR 6-WEEK SCOPE
Unitree Go2 quadruped
RGB-D + 3D LiDAR
Flat-ground following
Tubing-management arm
Stair detection
Stair-aware gait switch
2 ft following on stairs
Payload < 8 lb stability
USF Hackathon 2026
02 · Scope

## Slide 4
The work
04 / 11
THREE THINGS TO SOLVE
A
See the staircase.
Detect stair geometry from fused RGB-D + LiDAR.
B
Switch the gait.
Walk → climb at the right moment. Then back.
C
Hold the 2 ft gap.
Stay close — but not too close — through vertical motion.
USF Hackathon 2026
03 · The work

## Slide 5
Architecture
05 / 11
SYSTEM LAYERS
From sensors to a foot on a step.
01
RGB-D · 3D LiDAR · sensor fusion
existing
02
Person tracking
existing
03
Stair detection & geometry
our work
04
Stair-aware follow + 2 ft controller
our work
05
Walk ↔ climb gait switching
our work
06
Go2 locomotion · payload mockup
existing
USF Hackathon 2026
04 · Architecture

## Slide 6
Final deliverables
06 / 11
WHAT WE SHIP BY JUN 29
Five artifacts. Each demo-able on its own.
01
Stair-following demo on the Go2
02
Stair-perception ROS 2 module
03
Stair-aware follow-policy patch
04
Isaac Sim test scene
05
Technical write-up + demo video
USF Hackathon 2026
05 · Deliverables

## Slide 7
Six-week plan
07 / 11
MAY 18 → JUN 29
One shippable thing every Friday.
W1
May 18–24
Kickoff &
setup
Repo, board, dev env
on 3 machines.
W2
May 25–31
Sensor
baseline
Bring up sensors,
reproduce flat-ground
follow.
W3
Jun 1–7
Stair
perception
Geometry detection,
sim test scene v1.
W4
Jun 8–14
Gait
switching
First end-to-end sim
climb. Mid-point
check.
W5
Jun 15–21
Hardware
bring-up
Deploy on Go2. Tune
the 2 ft gap.
W6
Jun 22–29
Demo &
write-up
Final demo Jun 29.
Video + report.
USF Hackathon 2026
06 · Plan

## Slide 8
Team
08 / 11
THE THREE OF US
Olga
Aibek
Chi Vo
SUPERVISORS
Dr. William Kearns · Prof. Yu Sun
Juan Ricardo Wilches · Hieu Tran · Temirzhan Mukhambet · Rice Pham · Khanh Quoc Duong
USF Hackathon 2026
07 · Team

## Slide 9
What we did this week
09 / 11
WEEK 1 COMPLETED
Everything in Done.
Created GitHub org (robotic-o2-team) and repo with project structure
Set up Sprint Board — 5 issues created, tracked, and completed
Studied project abstract and understood system architecture
Met with Dr. Kearns — clarified project scope and requirements
Contacted teammates, exchanged contacts, shared GitHub access
Researched related work and existing codebase
Set up development environments on all machines
Prepared and delivered this presentation
USF Hackathon 2026
08 · Status

## Slide 10
Risks
10 / 11
WHAT COULD DERAIL US
Hardware access slips
Sim-first. Hardware in W5–6.
Stairs vary a lot
Parametric Isaac Sim staircase.
Payload shifts balance
Mass-on / mass-off tests each milestone.
2 ft gap is tight
Conservative speed. "Hold & signal" fallback.
Team is part-time
Friday demo cadence. GitHub-tracked.
USF Hackathon 2026
09 · Risks

## Slide 11
Thank you
11 / 11
QUESTIONS?
A robot dog.
A flight of stairs.
Six weeks.
github.com/robotic-o2-team
Next milestone · Week 2: Sensor baseline